## Sheet1
COSC 310 Assignment 2 |  |  |  | due to the fact that we start the assignment last week, so we decide to use a combination of hour and date for our graph. We listed the specific time we will meet, and label the amount of work we have due in each phase. Each phase is label at the right and the subtask is label with a lighter color.
| Project Started: | 2021-02-27
|  |  |  | 2021-02-27 | [15 empty] | 2021-02-28 | [15 empty] | 2021-03-01 | [15 empty] | 2021-03-02 | [15 empty] | 2021-03-03 | [15 empty] | 2021-03-04 | [15 empty] | 2021-03-05
TASK | Assined: | START | END | 0.375 | 0.41667 | 0.45833 | 0.5 | 0.54167 | 0.58333 | 0.625 | 0.66667 | 0.70833 | 0.75 | 0.79167 | 0.83333 | 0.875 | 0.91667 | 0.95833 | 1 | 9AM | 10AM | 11AM | 12PM | 1PM | 2PM | 3PM | 4PM | 5PM | 6PM | 7PM | 8PM | 9PM | 10PM | 11PM | 12AM | 9AM | 10AM | 11AM | 12PM | 1PM | 2PM | 3PM | 4PM | 5PM | 6PM | 7PM | 8PM | 9PM | 10PM | 11PM | 12AM | 9AM | 10AM | 11AM | 12PM | 1PM | 2PM | 3PM | 4PM | 5PM | 6PM | 7PM | 8PM | 9PM | 10PM | 11PM | 12AM | 9AM | 10AM | 11AM | 12PM | 1PM | 2PM | 3PM | 4PM | 5PM | 6PM | 7PM | 8PM | 9PM | 10PM | 11PM | 12AM | 9AM | 10AM | 11AM | 12PM | 1PM | 2PM | 3PM | 4PM | 5PM | 6PM | 7PM | 8PM | 9PM | 10PM | 11PM | 12AM | 9AM | 10AM | 11AM | 12PM | 1PM | 2PM | 3PM | 4PM | 5PM | 6PM | 7PM | 8PM | 9PM | 10PM | 11PM | 12AM
1 Create Plan | [13 empty] | 100%
1.1 Create the charts necessary for effective planning |  | 2021-02-27 | 2021-02-28
1.1.1 WBS Chart | Ravi Bullock | 2021-02-27 | 2021-02-28
1.1.2 Gantt Chart | William Chen | 2021-02-27 | 2021-02-28
1.2 Decide how to divide up the work |  | 2021-02-27 | 2021-02-28
1.3 Set up the infructure necessary for collaboration |  | 2021-02-27 | 2021-02-28
1.3.1 Set up Github | Haneen Abu-Hijleh | 2021-02-27 | 2021-02-28
1.3.2 Set up Asana | Llya Yereferenko | 2021-02-27 | 2021-02-28
2 Research to Prepate for Coding |  | 2021-02-27 | 2021-02-28 | [25 empty] | 100%
2.1 Pick a programming language |  | 2021-02-27 | 2021-02-28
2.2 Research natural language processing libraries |  | 2021-02-27 | 2021-02-28
2.2.1 Pick A library |  | 2021-02-27 | 2021-02-28
2.2.1.1 Read documentation for the library |  | 2021-02-27 | 2021-02-28
2.3 Set up and harmonize development environments |  | 2021-02-27 | 2021-02-28
3 Code
3.1 Importing and testing library functionality |  | 2021-03-01 | 2021-03-02
3.2 Write a bank of sentences the bot can respond with |  | 2021-03-01 | 2021-03-02
3.3 Take input from the user |  | 2021-03-01 | 2021-03-02
3.3.1 Develop enough questions for 30 turns of dialogue |  | 2021-03-01 | 2021-03-02
3.3.2 Develop short dialogue chocies (handle conversation) |  | 2021-03-01 | 2021-03-02
3.4 Dynamically find keywords in the user input |  | 2021-03-01 | 2021-03-02
3.5 Pick appropriate responses to the input |  | 2021-03-01 | 2021-03-02
3.5.1 Connect each response with predefned keywords |  | 2021-03-01 | 2021-03-02
4 Evaluate Code
4.1 Test code |  | 2021-03-02 | 2021-03-04
4.1.1 Test if the program meets th requirement |  | 2021-03-02 | 2021-03-04
4.2 Identify limitations |  | 2021-03-02 | 2021-03-04
4.2.1 List the limitations of the sample output |  | 2021-03-02 | 2021-03-04
4.2.1.1 Identify how the limitations may be solved |  | 2021-03-02 | 2021-03-04
4.3 Make changes if necessary (back to coding phase) |  | 2021-03-02 | 2021-03-04
5 Record Presentation
5.1 Write script for presenation |  | 2021-03-04 | 2021-03-05
5.1.1 Control the time limite for the presentation |  | 2021-03-04 | 2021-03-05
5.1.2 give an overview of work distribution |  | 2021-03-04 | 2021-03-05
5.1.2.1 Hightlight the strengths and weakness of the program |  | 2021-03-04 | 2021-03-05
5.2 Make PM Graph from github |  | 2021-03-04 | 2021-03-05
5.3 Record presenation |  | 2021-03-04 | 2021-03-05
5.4 Write the README file for this project |  | 2021-03-04 | 2021-03-05
5.4.1 Describle how the program is orgainzed |  | 2021-03-04 | 2021-03-05
5.4.2 Develop a sample output |  | 2021-03-04 | 2021-03-05