## Sheet1
|  |  | 2021-02-27 | [15 empty] | 2021-02-28 | [15 empty] | 2021-03-01 | [15 empty] | 2021-03-02 | [15 empty] | 2021-03-03 | [15 empty] | 2021-03-04 | [15 empty] | 2021-03-05
TASK | START | END | 0.375 | 0.41667 | 0.45833 | 0.5 | 0.54167 | 0.58333 | 0.625 | 0.66667 | 0.70833 | 0.75 | 0.79167 | 0.83333 | 0.875 | 0.91667 | 0.95833 | 1 | 9AM | 10AM | 11AM | 12PM | 1PM | 2PM | 3PM | 4PM | 5PM | 6PM | 7PM | 8PM | 9PM | 10PM | 11PM | 12AM | 9AM | 10AM | 11AM | 12PM | 1PM | 2PM | 3PM | 4PM | 5PM | 6PM | 7PM | 8PM | 9PM | 10PM | 11PM | 12AM | 9AM | 10AM | 11AM | 12PM | 1PM | 2PM | 3PM | 4PM | 5PM | 6PM | 7PM | 8PM | 9PM | 10PM | 11PM | 12AM | 9AM | 10AM | 11AM | 12PM | 1PM | 2PM | 3PM | 4PM | 5PM | 6PM | 7PM | 8PM | 9PM | 10PM | 11PM | 12AM | 9AM | 10AM | 11AM | 12PM | 1PM | 2PM | 3PM | 4PM | 5PM | 6PM | 7PM | 8PM | 9PM | 10PM | 11PM | 12AM | 9AM | 10AM | 11AM | 12PM | 1PM | 2PM | 3PM | 4PM | 5PM | 6PM | 7PM | 8PM | 9PM | 10PM | 11PM | 12AM
1 Create Plan | [12 empty] | 100%
1.1 Create the charts necessary for effective planning | 2021-02-27 | 2021-02-28
1.1.1 WBS Chart | 2021-02-27 | 2021-02-28
1.1.2 Gantt Chart | 2021-02-27 | 2021-02-28
1.2 Decide how to divide up the work | 2021-02-27 | 2021-02-28
1.3 Set up the infructure necessary for collaboration | 2021-02-27 | 2021-02-28
1.3.1 Set up Github | 2021-02-27 | 2021-02-28
1.3.2 Set up Asana | 2021-02-27 | 2021-02-28
2 Research to Prepate for Coding | 2021-02-27 | 2021-02-28 | [25 empty] | 100%
2.1 Pick a programming language | 2021-02-27 | 2021-02-28
2.2 Research natural language processing libraries | 2021-02-27 | 2021-02-28
2.2.1 Pick A library | 2021-02-27 | 2021-02-28
2.2.1.1 Read documentation for the library | 2021-02-27 | 2021-02-28
2.3 Set up and harmonize development environments | 2021-02-27 | 2021-02-28
3 Code
3.1 Importing and testing library functionality | 2021-03-01 | 2021-03-02
3.2 Write a bank of sentences the bot can respond with | 2021-03-01 | 2021-03-02
3.3 Take input from the user | 2021-03-01 | 2021-03-02
3.3.1 Develop enough questions for 30 turns of dialogue | 2021-03-01 | 2021-03-02
3.3.2 Develop short dialogue chocies (handle conversation) | 2021-03-01 | 2021-03-02
3.4 Dynamically find keywords in the user input | 2021-03-01 | 2021-03-02
3.5 Pick appropriate responses to the input | 2021-03-01 | 2021-03-02
3.5.1 Connect each response with predefned keywords | 2021-03-01 | 2021-03-02
4 Evaluate Code
4.1 Test code | 2021-03-02 | 2021-03-04
4.1.1 Test if the program meets th requirement | 2021-03-02 | 2021-03-04
4.2 Identify limitations | 2021-03-02 | 2021-03-04
4.2.1 List the limitations of the sample output | 2021-03-02 | 2021-03-04
4.2.1.1 Identify how the limitations may be solved | 2021-03-02 | 2021-03-04
4.3 Make changes if necessary (back to coding phase) | 2021-03-02 | 2021-03-04
5 Record Presentation
5.1 Write script for presenation | 2021-03-04 | 2021-03-05
5.1.1 Control the time limite for the presentation | 2021-03-04 | 2021-03-05
5.1.2 give an overview of work distribution | 2021-03-04 | 2021-03-05
5.1.2.1 Hightlight the strengths and weakness of the program | 2021-03-04 | 2021-03-05
5.2 Make PM Graph from github | 2021-03-04 | 2021-03-05
5.3 Record presenation | 2021-03-04 | 2021-03-05
5.4 Write the README file for this project | 2021-03-04 | 2021-03-05
5.4.1 Describle how the program is orgainzed | 2021-03-04 | 2021-03-05
5.4.2 Develop a sample output | 2021-03-04 | 2021-03-05